## Sitemap & Page Plan
# | Phase | Cluster | URL | Page Title (H1) | Meta Title | Primary Keyword | Secondary Keywords | Schema Types | CTA Target | Notes
1 | Phase 1 (Wk 1-2) | Core | / | Spain Non-Lucrative Visa 2026 — Your Visa, Handled | Spain Non-Lucrative Visa 2026 — Apply Online with Spanish Lawyers ¦ My Spanish NLV | non lucrative visa spain | nlv spain, spain retirement visa, spain residence visa, live in spain without working | Organization, WebSite, WebPage, Service, Offer, BreadcrumbList, FAQPage | dashboard…/nlv | DONE — index.html
2 | Phase 1 (Wk 1-2) | Core | /pricing/ | Non-Lucrative Visa Pricing — Transparent Staged Payments | NLV Spain Pricing 2026 — €1,499 All-In ¦ My Spanish NLV | non lucrative visa spain cost | nlv spain price, how much does nlv cost, non lucrative visa fees | WebPage, Service, Offer, BreadcrumbList, FAQPage | dashboard…/nlv | Show 3-stage breakdown + renewal + family discount
3 | Phase 1 (Wk 1-2) | Core | /how-it-works/ | How It Works — 5-Step Dashboard Process | How to Apply for Spain's NLV — Step-by-Step ¦ My Spanish NLV | how to apply for non lucrative visa spain | nlv application process, non lucrative visa steps | WebPage, HowTo, BreadcrumbList | dashboard…/nlv | Dashboard screenshots, timeline, milestone payments
4 | Phase 1 (Wk 1-2) | Services | /services/non-lucrative-visa-application/ | Non-Lucrative Visa Application Service | Apply for Spain's Non-Lucrative Visa — Full Service ¦ My Spanish NLV | non lucrative visa application spain | apply for nlv, nlv application service, spain visa lawyers | Service, Offer, LegalService, BreadcrumbList | dashboard…/nlv | Main conversion page — detailed service breakdown
5 | Phase 1 (Wk 1-2) | Services | /services/non-lucrative-visa-renewal/ | Non-Lucrative Visa Renewal Service | Renew Your Spain NLV — €699 All-In ¦ My Spanish NLV | non lucrative visa renewal spain | renew nlv spain, nlv renewal service, nlv renewal cost | Service, Offer, LegalService, BreadcrumbList | dashboard…/nlv-renewal | Renewal conversion page — €300 + €399 breakdown
6 | Phase 1 (Wk 1-2) | Core | /book-a-call/ | Book a Free Call with Our Immigration Team | Book a Call — Free NLV Consultation ¦ My Spanish NLV | non lucrative visa consultation | speak to nlv lawyer, free visa consultation spain | WebPage, BreadcrumbList | Calendar embed | Lead capture for people not ready to start online
7 | Phase 2 (Wk 3-6) | Requirements | /requirements/ | Non-Lucrative Visa Requirements 2026 | Spain NLV Requirements 2026 — Full Checklist ¦ My Spanish NLV | non lucrative visa requirements spain | nlv requirements 2026, spain nlv requirements, what do i need for nlv | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | Pillar hub — links to all requirement spokes
8 | Phase 2 (Wk 3-6) | Requirements | /requirements/income-requirements/ | NLV Income Requirements — How Much Do You Need? | NLV Income Requirements 2026 — IPREM Calculator ¦ My Spanish NLV | non lucrative visa income requirements | nlv income, how much income for nlv spain, 400% iprem nlv | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | Include IPREM calculator widget — ~€2,400/mo + €600 per dependent
9 | Phase 2 (Wk 3-6) | Requirements | /requirements/savings-requirements/ | NLV Savings Requirements — Proving Your Finances | NLV Savings Requirements — How Much in the Bank? ¦ My Spanish NLV | nlv savings requirements spain | how much savings for nlv, bank balance for non lucrative visa | WebPage, BreadcrumbList | dashboard…/nlv | Lump sum alternative to monthly income
10 | Phase 2 (Wk 3-6) | Requirements | /requirements/passive-income/ | Passive Income for the NLV — What Qualifies? | Passive Income for Spain's NLV — What Counts? ¦ My Spanish NLV | passive income non lucrative visa | passive income nlv spain, rental income for nlv, dividends nlv | WebPage, BreadcrumbList | dashboard…/nlv | Rental income, dividends, investments, royalties
11 | Phase 2 (Wk 3-6) | Requirements | /requirements/pension-income/ | Using Your Pension for Spain's NLV | Pension Income for NLV Spain — State & Private ¦ My Spanish NLV | pension non lucrative visa spain | retire to spain on pension, pension income nlv, state pension spain nlv | WebPage, BreadcrumbList | dashboard…/nlv | State pension, private pension, combination
12 | Phase 2 (Wk 3-6) | Requirements | /requirements/bank-statements/ | Bank Statements for the NLV — What's Required | NLV Bank Statement Requirements ¦ My Spanish NLV | bank statements non lucrative visa | nlv bank statements, how many months bank statements nlv | WebPage, BreadcrumbList | dashboard…/nlv | How many months, apostille, what they look for
13 | Phase 2 (Wk 3-6) | Requirements | /requirements/document-checklist/ | NLV Document Checklist 2026 — Everything You Need | NLV Document Checklist 2026 — Downloadable PDF ¦ My Spanish NLV | non lucrative visa document checklist | nlv documents needed, nlv checklist spain | WebPage, BreadcrumbList | PDF download + dashboard…/nlv | Lead magnet — downloadable PDF checklist
14 | Phase 2 (Wk 3-6) | Requirements | /requirements/criminal-record-certificate/ | Criminal Record Certificate for the NLV | Criminal Record Check for Spain's NLV ¦ My Spanish NLV | criminal record certificate nlv spain | police check nlv, dbs for spain visa, fbi background check nlv | WebPage, BreadcrumbList | dashboard…/nlv | Country-specific instructions (ACRO, FBI, etc.)
15 | Phase 2 (Wk 3-6) | Requirements | /requirements/medical-certificate/ | Medical Certificate for the NLV | Medical Certificate for Non-Lucrative Visa Spain ¦ My Spanish NLV | medical certificate non lucrative visa | nlv medical certificate, doctor letter nlv spain | WebPage, BreadcrumbList | dashboard…/nlv | What the certificate must say, how recent
16 | Phase 2 (Wk 3-6) | Requirements | /requirements/health-insurance-requirement/ | Health Insurance Requirements for the NLV | NLV Health Insurance Requirements — No Co-Pays ¦ My Spanish NLV | health insurance non lucrative visa spain | nlv health insurance requirements, no copay insurance nlv | WebPage, FAQPage, BreadcrumbList | spanish-healthinsurance.com | #1 rejection reason — links to insurance partner
17 | Phase 2 (Wk 3-6) | Process | /application-process/ | NLV Application Process — Step by Step | How to Apply for Spain's NLV — Full Process Guide ¦ My Spanish NLV | non lucrative visa application process | nlv process, how to get nlv spain, nlv step by step | WebPage, HowTo, BreadcrumbList | dashboard…/nlv | Pillar hub — links to all process spokes
18 | Phase 2 (Wk 3-6) | Process | /application-process/step-by-step-guide/ | NLV Step-by-Step Application Guide | NLV Application Step-by-Step Guide 2026 ¦ My Spanish NLV | non lucrative visa step by step | nlv application guide, how to apply nlv spain step by step | WebPage, HowTo, BreadcrumbList | dashboard…/nlv | Detailed walkthrough of every stage
19 | Phase 2 (Wk 3-6) | Process | /application-process/consulate-appointment/ | Booking Your NLV Consulate Appointment | NLV Consulate Appointment — How to Book ¦ My Spanish NLV | nlv consulate appointment spain | book consulate appointment nlv, spanish consulate visa appointment | WebPage, BreadcrumbList | dashboard…/nlv | Consulate-specific booking info
20 | Phase 2 (Wk 3-6) | Process | /application-process/processing-time/ | NLV Processing Time — How Long Does It Take? | NLV Processing Time 2026 — 1 to 3 Months ¦ My Spanish NLV | non lucrative visa processing time | how long does nlv take, nlv waiting time, nlv approval time | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | Realistic timelines by consulate
21 | Phase 2 (Wk 3-6) | Process | /application-process/what-happens-after-approval/ | What Happens After Your NLV Is Approved | After NLV Approval — Next Steps in Spain ¦ My Spanish NLV | after nlv approval spain | nlv approved what next, move to spain after nlv, 90 days to enter spain | WebPage, BreadcrumbList | dashboard…/nlv | 90-day entry window, empadronamiento, TIE
22 | Phase 2 (Wk 3-6) | Process | /application-process/nie-tie-after-nlv/ | Getting Your NIE and TIE After Arriving in Spain | NIE & TIE After NLV Approval — What You Need ¦ My Spanish NLV | nie tie after nlv spain | nie number after nlv, tie card spain nlv, foreigner identity card spain | WebPage, BreadcrumbList | dashboard…/nlv | NIE vs TIE explained, how to book cita previa
23 | Phase 2 (Wk 3-6) | Process | /application-process/empadronamiento-after-arrival/ | Empadronamiento — Registering Your Address in Spain | Empadronamiento After NLV — Town Hall Registration ¦ My Spanish NLV | empadronamiento nlv spain | register address spain, padron spain, empadronamiento for visa | WebPage, BreadcrumbList | dashboard…/nlv | Required for TIE and residency — how to do it
24 | Phase 2 (Wk 3-6) | Health Insurance | /health-insurance/ | Health Insurance for Spain's Non-Lucrative Visa | NLV Health Insurance — Best Policies for 2026 ¦ My Spanish NLV | health insurance non lucrative visa | best health insurance nlv spain, nlv insurance, private health insurance spain visa | WebPage, FAQPage, BreadcrumbList | spanish-healthinsurance.com | Pillar hub — big upsell to insurance partner
25 | Phase 2 (Wk 3-6) | Health Insurance | /health-insurance/best-health-insurance-for-nlv/ | Best Health Insurance for the NLV in 2026 | Best Health Insurance for NLV Spain 2026 ¦ My Spanish NLV | best health insurance for nlv spain | top nlv insurance providers, recommended nlv health insurance | WebPage, BreadcrumbList | spanish-healthinsurance.com | Comparison article — drives affiliate traffic
26 | Phase 2 (Wk 3-6) | Health Insurance | /health-insurance/no-copay-health-insurance/ | No-Copay Health Insurance for Spain Visas | No Copay Health Insurance for NLV — Why It Matters ¦ My Spanish NLV | no copay health insurance spain visa | no copay insurance nlv, full coverage insurance spain | WebPage, BreadcrumbList | spanish-healthinsurance.com | Explains the no-copay requirement — key rejection reason
27 | Phase 2 (Wk 3-6) | Health Insurance | /health-insurance/insurance-mistakes-that-fail-nlv/ | Health Insurance Mistakes That Get Your NLV Rejected | Insurance Mistakes That Fail NLV Applications ¦ My Spanish NLV | nlv rejected health insurance | nlv insurance mistakes, why nlv rejected, insurance rejection nlv | WebPage, BreadcrumbList | spanish-healthinsurance.com | Common mistakes — travel insurance, copays, exclusions
28 | Phase 2 (Wk 3-6) | Renewal | /renewal/ | Non-Lucrative Visa Renewal — Everything You Need to Know | NLV Renewal Spain 2026 — Full Guide ¦ My Spanish NLV | non lucrative visa renewal spain | renew nlv, nlv renewal requirements, nlv renewal process | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv-renewal | Pillar hub for renewal cluster
29 | Phase 2 (Wk 3-6) | Renewal | /renewal/how-to-renew-nlv/ | How to Renew Your NLV — Step by Step | How to Renew NLV Spain — Step-by-Step Guide ¦ My Spanish NLV | how to renew non lucrative visa spain | nlv renewal process, renew nlv step by step | WebPage, HowTo, BreadcrumbList | dashboard…/nlv-renewal | Timeline, when to start, what changes from initial
30 | Phase 2 (Wk 3-6) | Renewal | /renewal/renewal-requirements/ | NLV Renewal Requirements 2026 | NLV Renewal Requirements — What's Changed ¦ My Spanish NLV | nlv renewal requirements 2026 | requirements to renew nlv, nlv renewal documents needed | WebPage, BreadcrumbList | dashboard…/nlv-renewal | Updated requirements for renewal vs initial
31 | Phase 2 (Wk 3-6) | Renewal | /renewal/long-term-residency-after-nlv/ | Long-Term Residency & Citizenship After the NLV | NLV to Permanent Residency — 5-Year Path ¦ My Spanish NLV | nlv to permanent residency spain | long term residency after nlv, citizenship after nlv, 5 years permanent residency spain | WebPage, BreadcrumbList | dashboard…/nlv-renewal | 1+2+2 structure → PR at 5yrs → citizenship at 10yrs
32 | Phase 2 (Wk 3-6) | Services | /services/family-application/ | NLV Family Application — Spouse & Children | NLV for Families — Spouse, Children & Dependants ¦ My Spanish NLV | non lucrative visa family spain | nlv spouse, nlv children, nlv dependants, family nlv application | Service, Offer, BreadcrumbList | dashboard…/nlv | Family discount, +€600/mo per dependent, joint applications
33 | Phase 2 (Wk 3-6) | Services | /services/appeal-rejected-nlv/ | NLV Rejected? How to Appeal or Reapply | NLV Rejected — Appeal & Reapply Service ¦ My Spanish NLV | non lucrative visa rejected spain | nlv rejected, appeal nlv spain, nlv denied what to do | Service, LegalService, BreadcrumbList | dashboard…/nlv | Recovery service for rejected applications
34 | Phase 3 (Wk 7-10) | By Country | /by-country/ | NLV by Country — Consulate Guides | NLV by Country — Apply from the USA, UK, Canada & More ¦ My Spanish NLV | non lucrative visa from [country] | nlv from usa, nlv from uk, nlv from canada | WebPage, BreadcrumbList | dashboard…/nlv | Hub page linking to all country guides
35 | Phase 3 (Wk 7-10) | By Country | /by-country/from-usa/ | Non-Lucrative Visa from the USA | NLV from the USA — American's Guide to Spain ¦ My Spanish NLV | non lucrative visa from usa | nlv from america, spain retirement visa usa, american retiring in spain | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | US-specific: FBI check, apostille, consulate locations
36 | Phase 3 (Wk 7-10) | By Country | /by-country/from-uk/ | Non-Lucrative Visa from the UK | NLV from the UK — British Guide to Spain ¦ My Spanish NLV | non lucrative visa from uk | nlv from britain, spain visa for british, retire to spain from uk | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | Post-Brexit rules, BLS centres, ACRO certificate
37 | Phase 3 (Wk 7-10) | By Country | /by-country/from-canada/ | Non-Lucrative Visa from Canada | NLV from Canada — Canadian's Guide to Spain ¦ My Spanish NLV | non lucrative visa from canada | nlv from canada, canadian retiring in spain, spain visa for canadians | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | RCMP check, Canadian consulate specifics
38 | Phase 3 (Wk 7-10) | By Country | /by-country/from-australia/ | Non-Lucrative Visa from Australia | NLV from Australia — Aussie Guide to Spain ¦ My Spanish NLV | non lucrative visa from australia | nlv from australia, australian retiring in spain | WebPage, BreadcrumbList | dashboard…/nlv | AFP check, Canberra consulate
39 | Phase 3 (Wk 7-10) | By Country | /by-country/from-south-africa/ | Non-Lucrative Visa from South Africa | NLV from South Africa — SA Guide to Spain ¦ My Spanish NLV | non lucrative visa from south africa | nlv south africa, south african moving to spain | WebPage, BreadcrumbList | dashboard…/nlv | SAPS clearance, Pretoria consulate
40 | Phase 3 (Wk 7-10) | By Country | /by-country/from-ireland-non-eu/ | Non-Lucrative Visa for Non-EU Irish Residents | NLV from Ireland (Non-EU Nationals) ¦ My Spanish NLV | non lucrative visa from ireland | nlv ireland non eu, non eu in ireland moving to spain | WebPage, BreadcrumbList | dashboard…/nlv | For non-EU nationals living in Ireland
41 | Phase 3 (Wk 7-10) | By Country | /by-country/from-new-zealand/ | Non-Lucrative Visa from New Zealand | NLV from New Zealand — Kiwi Guide to Spain ¦ My Spanish NLV | non lucrative visa from new zealand | nlv new zealand, kiwi moving to spain | WebPage, BreadcrumbList | dashboard…/nlv | NZ police check, Wellington consulate
42 | Phase 3 (Wk 7-10) | For (Persona) | /for/retirees/ | Non-Lucrative Visa for Retirees | NLV for Retirees — Retire to Spain in 2026 ¦ My Spanish NLV | spain retirement visa | retire to spain, non lucrative visa retirees, best visa to retire to spain | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | Pension income, healthcare, cost of living, best cities
43 | Phase 3 (Wk 7-10) | For (Persona) | /for/early-retirees-fire/ | NLV for Early Retirees & FIRE | NLV for FIRE & Early Retirement in Spain ¦ My Spanish NLV | fire retire to spain | early retirement spain, fire movement spain, retire early spain visa | WebPage, BreadcrumbList | dashboard…/nlv | Investment income, 4% rule meets IPREM, young retiree angle
44 | Phase 3 (Wk 7-10) | For (Persona) | /for/families/ | NLV for Families — Move to Spain Together | NLV for Families — Relocate to Spain with Kids ¦ My Spanish NLV | move to spain with family visa | nlv family, move to spain with children, family relocation spain | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | Property equity families, income per dependent, schools, family discount
45 | Phase 3 (Wk 7-10) | For (Persona) | /for/sabbatical/ | NLV for a Career Break or Sabbatical | NLV for Sabbaticals — Live in Spain for a Year ¦ My Spanish NLV | sabbatical in spain visa | career break spain, take a year off in spain, sabbatical visa spain | WebPage, BreadcrumbList | dashboard…/nlv | 1-year initial visa, savings-based, no work restriction explanation
46 | Phase 4 (Wk 11-12) | Tax | /tax/ | Tax on the Non-Lucrative Visa — What You Need to Know | NLV Tax Guide Spain 2026 ¦ My Spanish NLV | tax on non lucrative visa spain | nlv tax, do you pay tax on nlv spain, tax residency nlv | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | Pillar hub for tax cluster
47 | Phase 4 (Wk 11-12) | Tax | /tax/tax-residency-on-nlv/ | Tax Residency on the NLV — 183-Day Rule | NLV Tax Residency — When You Become Spanish Tax Resident ¦ My Spanish NLV | nlv tax residency spain | 183 day rule spain, tax resident on nlv, when do i pay spanish tax | WebPage, BreadcrumbList | dashboard…/nlv | 183-day rule, worldwide income, Modelo 100
48 | Phase 4 (Wk 11-12) | Tax | /tax/pension-tax-in-spain/ | How Your Pension Is Taxed in Spain | Pension Tax in Spain for NLV Holders ¦ My Spanish NLV | pension tax spain nlv | is my pension taxed in spain, uk pension spain tax, us social security spain tax | WebPage, BreadcrumbList | dashboard…/nlv | Double taxation treaties by country
49 | Phase 4 (Wk 11-12) | Compare | /compare/nlv-vs-digital-nomad-visa/ | NLV vs Digital Nomad Visa — Which Is Right for You? | NLV vs DNV Spain — Comparison Guide ¦ My Spanish NLV | nlv vs digital nomad visa spain | non lucrative visa vs dnv, which spain visa, nlv or dnv | WebPage, FAQPage, BreadcrumbList | myspanishdnv.com + dashboard…/nlv | Side-by-side comparison, decision tree
50 | Phase 4 (Wk 11-12) | Compare | /compare/nlv-vs-golden-visa/ | NLV vs Golden Visa — Which Should You Choose? | NLV vs Golden Visa Spain — Comparison ¦ My Spanish NLV | nlv vs golden visa spain | non lucrative visa vs golden visa, spain investor visa vs retirement visa | WebPage, BreadcrumbList | dashboard…/nlv | Cost comparison, requirements, benefits
51 | Phase 4 (Wk 11-12) | Compare | /compare/spain-nlv-vs-portugal-d7/ | Spain NLV vs Portugal D7 Visa | Spain NLV vs Portugal D7 — Which Country? ¦ My Spanish NLV | spain nlv vs portugal d7 | spain vs portugal retirement visa, nlv or d7 visa | WebPage, BreadcrumbList | dashboard…/nlv | Country comparison — cost of living, tax, process
52 | Phase 4 (Wk 11-12) | Rejection | /rejection/common-reasons-for-rejection/ | Common Reasons NLV Applications Get Rejected | NLV Rejection Reasons — Avoid These Mistakes ¦ My Spanish NLV | nlv rejected reasons spain | why was my nlv rejected, common nlv rejection reasons, nlv application denied | WebPage, FAQPage, BreadcrumbList | dashboard…/nlv | Insurance, income, documents — prevention guide
53 | Phase 4 (Wk 11-12) | Rejection | /rejection/how-to-appeal/ | How to Appeal a Rejected NLV | NLV Appeal Process — What to Do If Rejected ¦ My Spanish NLV | appeal nlv rejection spain | how to appeal nlv, nlv appeal process, nlv rejected appeal | WebPage, BreadcrumbList | dashboard…/nlv | Legal process, timelines, success rates
54 | Phase 5 (Wk 9-12+) | Life in Spain | /life-in-spain/best-cities-for-retirees/ | Best Cities in Spain for Retirees | Best Cities to Retire in Spain 2026 ¦ My Spanish NLV | best cities to retire in spain | where to retire in spain, best places to live in spain for retirees | WebPage, BreadcrumbList | dashboard…/nlv | Valencia, Malaga, Alicante, Barcelona, Madrid pros/cons
55 | Phase 5 (Wk 9-12+) | Life in Spain | /life-in-spain/cost-of-living/ | Cost of Living in Spain for Expats | Cost of Living in Spain 2026 — Expat Guide ¦ My Spanish NLV | cost of living spain expat | how much to live in spain, spain cost of living retiree, monthly budget spain | WebPage, BreadcrumbList | dashboard…/nlv | Monthly budgets by city, meets IPREM context
56 | Phase 5 (Wk 9-12+) | Life in Spain | /life-in-spain/healthcare-system/ | Spain's Healthcare System for NLV Holders | Healthcare in Spain for NLV Residents ¦ My Spanish NLV | healthcare system spain expat | spanish healthcare for expats, public vs private healthcare spain | WebPage, BreadcrumbList | spanish-healthinsurance.com | Public vs private, convenio especial, insurance bridge
57 | Phase 5 (Wk 9-12+) | Life in Spain | /life-in-spain/buying-property-on-nlv/ | Can You Buy Property on the NLV? | Buying Property in Spain on an NLV ¦ My Spanish NLV | buy property spain nlv | can i buy a house on nlv, property purchase spain visa | WebPage, BreadcrumbList | dashboard…/nlv | Yes you can, NIE required, no residency needed to buy
58 | Phase 5 (Wk 9-12+) | About | /about/ | About My Spanish NLV | About Us — My Spanish NLV ¦ Powered by Platinum Legal Spain | my spanish nlv | who is my spanish nlv, platinum legal spain nlv | WebPage, Organization, BreadcrumbList | dashboard…/nlv | Trust signals, PLS credentials, team
59 | Phase 5 (Wk 9-12+) | Legal | /legal/privacy-policy/ | Privacy Policy | Privacy Policy ¦ My Spanish NLV |  |  | WebPage |  | Standard GDPR-compliant privacy policy
60 | Phase 5 (Wk 9-12+) | Legal | /legal/terms-of-service/ | Terms of Service | Terms of Service ¦ My Spanish NLV |  |  | WebPage |  | Standard ToS
61 | Phase 5 (Wk 9-12+) | Legal | /legal/cookie-policy/ | Cookie Policy | Cookie Policy ¦ My Spanish NLV |  |  | WebPage |  | Cookie consent + policy
62 | Phase 5 (Wk 9-12+) | Legal | /legal/refund-policy/ | Refund Policy | Refund Policy ¦ My Spanish NLV |  |  | WebPage |  | Critical for trust — €400 upfront payment

## Phase Summary
Phase | Pages | Focus
Phase 1 (Wk 1-2) | 6 | Homepage, pricing, how it works, main service pages, book-a-call
Phase 2 (Wk 3-6) | 27 | Requirements cluster, process cluster, health insurance cluster, renewal cluster, family + rejection services
Phase 3 (Wk 7-10) | 12 | Country/consulate pages (USA, UK, Canada, etc.) + persona pages (retirees, FIRE, families, sabbatical)
Phase 4 (Wk 11-12) | 8 | Tax cluster, comparison pages (vs DNV, Golden Visa, Portugal D7), rejection/appeal
Phase 5 (Wk 9-12+) | 9 | Life in Spain content, about, legal pages, blog launch
TOTAL